## README
Item | Detail
What this is | Synthetic sample data for a Power BI deployment readiness dashboard (portfolio project). All names and figures are made up.
Sheets | Sites, ReadinessTasks, Risks, AI_Report_Checks
Relationships | Sites[SiteID] one-to-many with ReadinessTasks[SiteID], Risks[SiteID] and AI_Report_Checks[SiteID]
Snapshot date | 'Today' in this data is 23 October 2026

## Sites
SiteID | SiteName | Region | Wave | PlannedGoLive | DeploymentLead
S01 | Limerick | Ireland | Wave 1 | 2026-09-07 | P. Ryan
S02 | Athlone | Ireland | Wave 1 | 2026-10-05 | J. Walsh
S03 | Dundalk | Ireland | Wave 1 | 2026-11-02 | S. Kelly
S04 | Austin | USA | Wave 2 | 2026-11-30 | A. Murphy
S05 | Raleigh | USA | Wave 2 | 2026-12-28 | A. Murphy
S06 | Singapore | Singapore | Wave 2 | 2027-01-25 | A. Murphy
S07 | Eindhoven | Netherlands | Wave 3 | 2027-02-22 | P. Ryan
S08 | Heredia | Costa Rica | Wave 3 | 2027-03-22 | A. Murphy

## ReadinessTasks
TaskID | SiteID | Workstream | Task | PlannedDate | CompletedDate | Status
T0001 | S01 | Training | Super-user training | 2026-06-23 | 2026-06-20 | Complete
T0002 | S01 | Training | End-user training | 2026-07-09 | 2026-07-11 | Complete
T0003 | S01 | Training | Training sign-off | 2026-07-22 | 2026-07-18 | Complete
T0004 | S01 | Process | Current-state process mapped | 2026-06-24 | 2026-06-26 | Complete
T0005 | S01 | Process | Gap analysis vs standard | 2026-07-13 | 2026-07-09 | Complete
T0006 | S01 | Process | Future-state SOPs approved | 2026-07-30 | 2026-07-26 | Complete
T0007 | S01 | Systems | User access set up | 2026-06-18 | 2026-06-17 | Complete
T0008 | S01 | Systems | Integration tested | 2026-07-07 | 2026-07-19 | Complete
T0009 | S01 | Systems | Cutover plan approved | 2026-07-22 | 2026-08-03 | Complete
T0010 | S01 | Data Migration | Data extract | 2026-06-25 | 2026-07-08 | Complete
T0011 | S01 | Data Migration | Data cleansing | 2026-07-12 | 2026-07-18 | Complete
T0012 | S01 | Data Migration | Mock load | 2026-07-22 | 2026-07-19 | Complete
T0013 | S01 | Data Migration | Final load validated | 2026-08-17 | 2026-08-18 | Complete
T0014 | S01 | Validation | IQ/OQ complete | 2026-06-22 | 2026-06-30 | Complete
T0015 | S01 | Validation | PQ complete | 2026-07-08 | 2026-07-17 | Complete
T0016 | S01 | Validation | Validation report signed | 2026-07-26 | 2026-07-26 | Complete
T0017 | S02 | Training | Super-user training | 2026-07-16 | 2026-07-20 | Complete
T0018 | S02 | Training | End-user training | 2026-08-08 | 2026-08-13 | Complete
T0019 | S02 | Training | Training sign-off | 2026-08-25 | 2026-08-22 | Complete
T0020 | S02 | Process | Current-state process mapped | 2026-07-14 | 2026-07-14 | Complete
T0021 | S02 | Process | Gap analysis vs standard | 2026-08-05 | 2026-08-15 | Complete
T0022 | S02 | Process | Future-state SOPs approved | 2026-08-24 | 2026-08-21 | Complete
T0023 | S02 | Systems | User access set up | 2026-07-21 | 2026-07-26 | Complete
T0024 | S02 | Systems | Integration tested | 2026-08-05 | 2026-08-19 | Complete
T0025 | S02 | Systems | Cutover plan approved | 2026-08-25 | 2026-09-03 | Complete
T0026 | S02 | Data Migration | Data extract | 2026-07-14 | 2026-07-17 | Complete
T0027 | S02 | Data Migration | Data cleansing | 2026-08-07 | 2026-08-04 | Complete
T0028 | S02 | Data Migration | Mock load | 2026-08-18 | 2026-08-22 | Complete
T0029 | S02 | Data Migration | Final load validated | 2026-09-15 | 2026-09-24 | Complete
T0030 | S02 | Validation | IQ/OQ complete | 2026-07-17 | 2026-07-23 | Complete
T0031 | S02 | Validation | PQ complete | 2026-07-31 |  | Overdue
T0032 | S02 | Validation | Validation report signed | 2026-08-23 | 2026-08-21 | Complete
T0033 | S03 | Training | Super-user training | 2026-08-17 | 2026-08-21 | Complete
T0034 | S03 | Training | End-user training | 2026-08-30 |  | Overdue
T0035 | S03 | Training | Training sign-off | 2026-09-21 | 2026-10-01 | Complete
T0036 | S03 | Process | Current-state process mapped | 2026-08-11 | 2026-08-18 | Complete
T0037 | S03 | Process | Gap analysis vs standard | 2026-09-05 | 2026-09-04 | Complete
T0038 | S03 | Process | Future-state SOPs approved | 2026-09-21 |  | Overdue
T0039 | S03 | Systems | User access set up | 2026-08-14 |  | Overdue
T0040 | S03 | Systems | Integration tested | 2026-09-02 |  | Overdue
T0041 | S03 | Systems | Cutover plan approved | 2026-09-21 |  | Overdue
T0042 | S03 | Data Migration | Data extract | 2026-08-12 | 2026-08-11 | Complete
T0043 | S03 | Data Migration | Data cleansing | 2026-08-31 |  | Overdue
T0044 | S03 | Data Migration | Mock load | 2026-09-15 | 2026-09-28 | Complete
T0045 | S03 | Data Migration | Final load validated | 2026-10-05 | 2026-09-30 | Complete
T0046 | S03 | Validation | IQ/OQ complete | 2026-08-12 | 2026-08-18 | Complete
T0047 | S03 | Validation | PQ complete | 2026-09-06 |  | Overdue
T0048 | S03 | Validation | Validation report signed | 2026-09-17 |  | Overdue
T0049 | S04 | Training | Super-user training | 2026-09-15 |  | Overdue
T0050 | S04 | Training | End-user training | 2026-10-05 | 2026-10-01 | Complete
T0051 | S04 | Training | Training sign-off | 2026-10-20 |  | Overdue
T0052 | S04 | Process | Current-state process mapped | 2026-09-17 | 2026-09-24 | Complete
T0053 | S04 | Process | Gap analysis vs standard | 2026-10-01 | 2026-09-29 | Complete
T0054 | S04 | Process | Future-state SOPs approved | 2026-10-20 | 2026-10-16 | Complete
T0055 | S04 | Systems | User access set up | 2026-09-10 | 2026-09-11 | Complete
T0056 | S04 | Systems | Integration tested | 2026-10-02 | 2026-10-07 | Complete
T0057 | S04 | Systems | Cutover plan approved | 2026-10-22 | 2026-10-17 | Complete
T0058 | S04 | Data Migration | Data extract | 2026-09-16 | 2026-09-14 | Complete
T0059 | S04 | Data Migration | Data cleansing | 2026-09-30 | 2026-09-27 | Complete
T0060 | S04 | Data Migration | Mock load | 2026-10-16 | 2026-10-15 | Complete
T0061 | S04 | Data Migration | Final load validated | 2026-11-10 |  | In progress
T0062 | S04 | Validation | IQ/OQ complete | 2026-09-12 | 2026-09-22 | Complete
T0063 | S04 | Validation | PQ complete | 2026-09-26 | 2026-10-06 | Complete
T0064 | S04 | Validation | Validation report signed | 2026-10-20 | 2026-10-23 | Complete
T0065 | S05 | Training | Super-user training | 2026-10-06 | 2026-10-11 | Complete
T0066 | S05 | Training | End-user training | 2026-10-27 |  | In progress
T0067 | S05 | Training | Training sign-off | 2026-11-12 |  | Not started
T0068 | S05 | Process | Current-state process mapped | 2026-10-08 |  | Overdue
T0069 | S05 | Process | Gap analysis vs standard | 2026-10-31 |  | In progress
T0070 | S05 | Process | Future-state SOPs approved | 2026-11-12 |  | Not started
T0071 | S05 | Systems | User access set up | 2026-10-13 | 2026-10-10 | Complete
T0072 | S05 | Systems | Integration tested | 2026-10-27 |  | In progress
T0073 | S05 | Systems | Cutover plan approved | 2026-11-12 |  | In progress
T0074 | S05 | Data Migration | Data extract | 2026-10-08 | 2026-10-19 | Complete
T0075 | S05 | Data Migration | Data cleansing | 2026-10-28 |  | Not started
T0076 | S05 | Data Migration | Mock load | 2026-11-19 |  | Not started
T0077 | S05 | Data Migration | Final load validated | 2026-12-01 |  | In progress
T0078 | S05 | Validation | IQ/OQ complete | 2026-10-08 | 2026-10-18 | Complete
T0079 | S05 | Validation | PQ complete | 2026-10-28 |  | Not started
T0080 | S05 | Validation | Validation report signed | 2026-11-10 |  | In progress
T0081 | S06 | Training | Super-user training | 2026-11-09 |  | In progress
T0082 | S06 | Training | End-user training | 2026-11-23 |  | In progress
T0083 | S06 | Training | Training sign-off | 2026-12-15 |  | In progress
T0084 | S06 | Process | Current-state process mapped | 2026-11-07 |  | Not started
T0085 | S06 | Process | Gap analysis vs standard | 2026-11-23 |  | Not started
T0086 | S06 | Process | Future-state SOPs approved | 2026-12-11 |  | In progress
T0087 | S06 | Systems | User access set up | 2026-11-05 |  | In progress
T0088 | S06 | Systems | Integration tested | 2026-11-23 |  | In progress
T0089 | S06 | Systems | Cutover plan approved | 2026-12-17 |  | Not started
T0090 | S06 | Data Migration | Data extract | 2026-11-09 |  | In progress
T0091 | S06 | Data Migration | Data cleansing | 2026-11-30 |  | Not started
T0092 | S06 | Data Migration | Mock load | 2026-12-18 |  | Not started
T0093 | S06 | Data Migration | Final load validated | 2027-01-01 |  | Not started
T0094 | S06 | Validation | IQ/OQ complete | 2026-11-09 |  | Not started
T0095 | S06 | Validation | PQ complete | 2026-11-26 |  | In progress
T0096 | S06 | Validation | Validation report signed | 2026-12-09 |  | In progress
T0097 | S07 | Training | Super-user training | 2026-12-07 |  | In progress
T0098 | S07 | Training | End-user training | 2026-12-19 |  | Not started
T0099 | S07 | Training | Training sign-off | 2027-01-07 |  | Not started
T0100 | S07 | Process | Current-state process mapped | 2026-11-30 |  | Not started
T0101 | S07 | Process | Gap analysis vs standard | 2026-12-27 |  | In progress
T0102 | S07 | Process | Future-state SOPs approved | 2027-01-15 |  | Not started
T0103 | S07 | Systems | User access set up | 2026-12-09 |  | In progress
T0104 | S07 | Systems | Integration tested | 2026-12-28 |  | In progress
T0105 | S07 | Systems | Cutover plan approved | 2027-01-07 |  | Not started
T0106 | S07 | Data Migration | Data extract | 2026-11-30 |  | Not started
T0107 | S07 | Data Migration | Data cleansing | 2026-12-28 |  | Not started
T0108 | S07 | Data Migration | Mock load | 2027-01-13 |  | Not started
T0109 | S07 | Data Migration | Final load validated | 2027-01-29 |  | Not started
T0110 | S07 | Validation | IQ/OQ complete | 2026-12-03 |  | Not started
T0111 | S07 | Validation | PQ complete | 2026-12-22 |  | Not started
T0112 | S07 | Validation | Validation report signed | 2027-01-09 |  | Not started
T0113 | S08 | Training | Super-user training | 2027-01-06 |  | In progress
T0114 | S08 | Training | End-user training | 2027-01-19 |  | In progress
T0115 | S08 | Training | Training sign-off | 2027-02-04 |  | Not started
T0116 | S08 | Process | Current-state process mapped | 2027-01-02 |  | In progress
T0117 | S08 | Process | Gap analysis vs standard | 2027-01-25 |  | In progress
T0118 | S08 | Process | Future-state SOPs approved | 2027-02-10 |  | Not started
T0119 | S08 | Systems | User access set up | 2027-01-05 |  | Not started
T0120 | S08 | Systems | Integration tested | 2027-01-23 |  | Not started
T0121 | S08 | Systems | Cutover plan approved | 2027-02-09 |  | Not started
T0122 | S08 | Data Migration | Data extract | 2027-01-06 |  | Not started
T0123 | S08 | Data Migration | Data cleansing | 2027-01-17 |  | Not started
T0124 | S08 | Data Migration | Mock load | 2027-02-04 |  | In progress
T0125 | S08 | Data Migration | Final load validated | 2027-03-01 |  | Not started
T0126 | S08 | Validation | IQ/OQ complete | 2027-01-05 |  | Not started
T0127 | S08 | Validation | PQ complete | 2027-01-20 |  | In progress
T0128 | S08 | Validation | Validation report signed | 2027-02-03 |  | Not started

## Risks
RiskID | SiteID | Workstream | Description | Severity | Status | RaisedDate | ClosedDate
R001 | S01 | Process | Local SOP differs from global standard | Low | Closed | 2026-09-13 | 2026-09-24
R002 | S01 | Data Migration | Master data quality below threshold | Medium | Closed | 2026-08-08 | 2026-08-17
R003 | S01 | Systems | Integration test failures | Low | Open | 2026-08-01
R004 | S02 | Process | Local SOP differs from global standard | Low | Closed | 2026-07-22 | 2026-08-28
R005 | S02 | Data Migration | Master data quality below threshold | Low | Open | 2026-08-15
R006 | S02 | Systems | Integration test failures | High | Open | 2026-08-08
R007 | S02 | Data Migration | Master data quality below threshold | Medium | Open | 2026-10-01
R008 | S02 | Data Migration | Master data quality below threshold | Medium | Closed | 2026-09-08 | 2026-09-28
R009 | S02 | Training | Super-users not released from production | High | Open | 2026-09-21
R010 | S03 | Systems | Integration test failures | Medium | Closed | 2026-09-30 | 2026-10-13
R011 | S03 | Process | Local SOP differs from global standard | Medium | Open | 2026-07-15
R012 | S03 | Data Migration | Master data quality below threshold | High | Open | 2026-09-28
R013 | S04 | Data Migration | Master data quality below threshold | Medium | Open | 2026-08-14
R014 | S04 | Process | Local SOP differs from global standard | High | Closed | 2026-09-03 | 2026-10-01
R015 | S04 | Systems | Integration test failures | High | Open | 2026-08-09
R016 | S05 | Systems | Integration test failures | Low | Open | 2026-08-13
R017 | S05 | Training | Super-users not released from production | High | Open | 2026-10-04
R018 | S05 | Training | Super-users not released from production | High | Closed | 2026-10-08 | 2026-10-15
R019 | S05 | Systems | Integration test failures | Medium | Closed | 2026-07-14 | 2026-08-15
R020 | S05 | Data Migration | Master data quality below threshold | Low | Open | 2026-09-29
R021 | S06 | Data Migration | Master data quality below threshold | High | Closed | 2026-07-21 | 2026-08-12
R022 | S06 | Process | Local SOP differs from global standard | Medium | Open | 2026-08-25
R023 | S06 | Training | Super-users not released from production | High | Closed | 2026-07-29 | 2026-08-19
R024 | S06 | Validation | Validation resource shortage | High | Closed | 2026-07-01 | 2026-07-22
R025 | S06 | Data Migration | Master data quality below threshold | Medium | Open | 2026-10-17
R026 | S06 | Systems | Integration test failures | High | Closed | 2026-07-31 | 2026-09-07
R027 | S07 | Process | Local SOP differs from global standard | Medium | Closed | 2026-09-15 | 2026-10-02
R028 | S07 | Systems | Integration test failures | Medium | Open | 2026-08-12
R029 | S08 | Validation | Validation resource shortage | High | Closed | 2026-07-24 | 2026-08-20
R030 | S08 | Systems | Integration test failures | Low | Open | 2026-10-14
R031 | S08 | Process | Local SOP differs from global standard | Medium | Open | 2026-08-14
R032 | S08 | Training | Super-users not released from production | Medium | Open | 2026-07-26
R033 | S08 | Data Migration | Master data quality below threshold | Medium | Open | 2026-08-10

## AI_Report_Checks
ReportID | ReportDate | SiteID | ReportType | ClaimsChecked | ErrorsFound | MainErrorType
AI019 | 2026-07-27 | S04 | Readiness summary | 15 | 2 | Wrong figure
AI022 | 2026-07-27 | S08 | Process comparison | 15 | 0 | None
AI011 | 2026-07-31 | S04 | Risk summary | 39 | 0 | None
AI028 | 2026-08-01 | S02 | Risk summary | 19 | 0 | None
AI021 | 2026-08-12 | S01 | Risk summary | 32 | 0 | None
AI008 | 2026-08-13 | S04 | Readiness summary | 24 | 0 | None
AI038 | 2026-08-18 | S02 | Risk summary | 26 | 0 | None
AI017 | 2026-08-18 | S07 | Risk summary | 37 | 2 | Outdated data
AI035 | 2026-08-19 | S05 | Process comparison | 21 | 1 | Wrong figure
AI001 | 2026-08-19 | S04 | Readiness summary | 25 | 0 | None
AI032 | 2026-08-21 | S05 | Process comparison | 29 | 0 | None
AI033 | 2026-08-24 | S02 | Risk summary | 21 | 3 | Hallucinated item
AI023 | 2026-08-25 | S02 | Risk summary | 31 | 3 | Outdated data
AI013 | 2026-09-01 | S01 | Process comparison | 15 | 1 | Hallucinated item
AI005 | 2026-09-04 | S05 | Risk summary | 22 | 3 | Outdated data
AI010 | 2026-09-04 | S08 | Process comparison | 31 | 0 | None
AI029 | 2026-09-10 | S05 | Risk summary | 33 | 0 | None
AI014 | 2026-09-14 | S04 | Readiness summary | 33 | 2 | Outdated data
AI006 | 2026-09-15 | S08 | Readiness summary | 20 | 0 | None
AI031 | 2026-09-18 | S02 | Risk summary | 21 | 2 | Outdated data
AI007 | 2026-09-18 | S01 | Process comparison | 26 | 1 | Hallucinated item
AI037 | 2026-09-19 | S03 | Risk summary | 35 | 0 | None
AI025 | 2026-09-20 | S02 | Process comparison | 22 | 3 | Outdated data
AI004 | 2026-09-20 | S03 | Readiness summary | 17 | 1 | Outdated data
AI039 | 2026-09-23 | S08 | Process comparison | 15 | 1 | Wrong figure
AI009 | 2026-09-25 | S03 | Readiness summary | 25 | 0 | None
AI026 | 2026-09-26 | S08 | Process comparison | 27 | 0 | None
AI002 | 2026-09-27 | S03 | Process comparison | 26 | 3 | Wrong figure
AI016 | 2026-10-03 | S03 | Readiness summary | 37 | 0 | None
AI015 | 2026-10-03 | S07 | Process comparison | 38 | 2 | Hallucinated item
AI020 | 2026-10-05 | S06 | Readiness summary | 27 | 2 | Hallucinated item
AI018 | 2026-10-05 | S01 | Risk summary | 33 | 1 | Outdated data
AI030 | 2026-10-05 | S08 | Readiness summary | 30 | 0 | None
AI003 | 2026-10-06 | S02 | Risk summary | 38 | 0 | None
AI024 | 2026-10-11 | S02 | Risk summary | 38 | 2 | Hallucinated item
AI034 | 2026-10-12 | S01 | Process comparison | 29 | 1 | Wrong figure
AI027 | 2026-10-13 | S05 | Readiness summary | 34 | 1 | Outdated data
AI036 | 2026-10-13 | S02 | Readiness summary | 38 | 1 | Outdated data
AI012 | 2026-10-22 | S05 | Readiness summary | 19 | 0 | None
AI040 | 2026-10-22 | S08 | Process comparison | 24 | 1 | Outdated data